## Launch Manager
No. | Assessment question | Assessment result | RGY | Recovery planning | Respons. | Due date
General Information
GI 1 | Have launch team responsibilities been clearly defined?
GI 2 | Have organization changes been included in HR and financial planning?
GI 3 | Have supplemental launch team resources been identified, timed and planned?
GI 4 | Has a dedicated staff level launch manager been identified for major launch activities?
GI 5 | Has the organization structure been evaluated for necessary changes?
GI 6 | Have plant objectives and customer expectations been clearly defined?
GI 7 | Have all plant procedures been reviewed to incorporate necessary changes resulting from product and process changes?
GI 8 | Is there a sense of urgency and intensity demonstrated through staff leadership and personal example?
GI 9 | Has an area been identified for the launch team including phone and comuter access?
GI 10 | Is there a methodical process which tracks assignments by department, person responsible and target completion dates? | [5 empty] | d
GI 11 | Does the plant have a communication plan to keep the workforce informed of launch status and progress towards objectives?
GI 12 | Is the plant aware of engineering program objectives and do they agreewith the plant's performance projections?
GI 13 | Have key event dates been summarized and are they reviewed on a regular basis to ensure changes are incorporated in launch planning activities?
Quality Planning
QP 1 | Has an APQP timing plan been completed?
QP 2 | Is the APQP plan regularly reviewed with a cross functional team to ensure progress and objectives are being met?
QP 3 | Are there any unresolved APQP issues which could significantly affect launch timing, quality or cost objectives?
QP 4 | Are there any open customer PPAP issues which will significantly affect launch timing, quality or cost?
QP 5 | Have these issues been formally documented to the program team?
Facility Planning
FP 1 | Has the facility transition plan been reviewed with the plant staff and union leadership?
Process Planning
PP 1 | Have salaried manning requirements been established from the start of pre-production training through production acceleration?
PP 4 | Is there a pre-production build plan that details the build requirements and the salaried and hourly people assigned to meet the requirements?
PP 5 | Is there a production build plan that details the build plan by day and shift and the salaried and hourly manning lineup to meet the requirements?
PP 6 | Does the production build plan include planned run time hours per shift, rate per hour goals, planned power builds, FGI objectives and customer shipping requirements?
PP 7 | Has a pre-production build process audit been planned to ensure that the operators understand the build instructions and quality requirements?
PP 8 | Is there a formal management system in place that allows the operators to make suggestions and / or improvements to process and product designs?
PP 9 | Are multiple, independent levels of management reviewing and approving every pre-production product?
PP 10 | Are RUN@RATE events being scheduled far enough in advance to protect customer requirements?
PP 11 | Are RUN@RATE events being used to test the entire system (end-of-line inspection, repair, material flow, FGI, shipping system etc.) not just the production process?
Material Planning
MP 1 | Has a supplier communication meeting been held at the plant to review program expectiations and requirements?
MP 2 | Have high risk suppliers been clearly identified and have they been put under focused review by supplier readiness, supplier development or purchasing?
MP 3 | Is the BOM audit conducted with a cross functional team from materials, quality, finance, industrial engineering and production?
MP 4 | Have the returnable packaging investments been included in the program investments?
MP 5 | Have FGI and shipping system disaster backup plans been tested to ensure there effectiveness?
MP 6 | Are FGI and shipping system personnel periodically trained on manual systems?
Change Management
CM 1 | Does the plant have a cross functional team that plans, controls, implements and verifies engineering change and authorized rework implementation?
CM 2 | Do the procedures include planning for good product breakpoints and identification?
CM 3 | Is there a management system for product engineering authorization and documentation of required reworks?
CM 4 | Are responsibilities for excess cost being appropriately allocated?
CM 5 | If the plant is expected to absorb excess cost, have the cost been included in the financial forecast?
CM 6 | Are there any open product issues that require rework that have not been formally authorized and documented?
CM 7 | Are there any open engineering change issues which will affect timing, quality or cost?
CM 8 | Have these issues been formally documented to the program and engineering team?
CM 9 | Does the program team and product engineering agree with the plant on open engineering issues?
CM 10 | Is the customer aware of pending engineering changes, the reason for the changes, and implementation timing?
CM 11 | Is there a communication system that reviews open issues on a regular basis with the plant, program teal and product engineering?
CM 12 | Are the appropriate people represented in these reviews?
CM 13 | Does the plant have an internal management system that effectively tracks plant related process quality and productivity issues?
CM 14 | Are there any open internal quality or productivity issues that will significantly affect launch timing, quality or cost?
Note on D1: Dr. Karl Stanger: enter R, G, or Y to color the cell

## Industrial Engineering
No. | Assessment question | Assessment result | RGY | Recovery planning | Respons. | Due date
General Information
GI 1 | Does the plant clearly understand engineering level content for each pre-production build event?
GI 2 | Has a schematic been completed which compares the customer production process and broadcast points to the company's production, FGI and shipping system?
GI 3 | Has the customer product system been physically walked to confirm understanding of broadcast points and product floats between broadcast points?
GI 4 | If the plant is not building to live broadcast, has the plant evaluated that the most efficient and reliable broadcast information is being utilized?
GI 5 | Have line speed increases or decreases and changes in the customer production or receiving process been evaluated for affects on broadcast window?
Quality Planning
QP 1 | Has a P-FMEA been completed with a cross functional team?
QP 2 | Is it a living document?
QP 3 | Has the P-FMEA seriously considered all error-proofing opportunities?
QP 4 | Has an error-proofing task matrix been completed to document issues, action planning and target dates for implementation? (The matrix should include but is not limited to: process location, issue, action plan, cost impact, labour impact, responsibility and target date)
QP 5 | Is there a management system that ensures new issues and lessons learned are promptly updated in the P-FMEA?
QP 6 | When a concern affects similar parts or processes are they reviewed and updated too?
QP 7 | Is there a schedule that periodically reviews and audits the P-FMEA (walk the process) to ensure production, test, error-proofing and inspection processes are comprehensive and are accurately represented in the P-FMEA?
QP 8 | Have drawings been reviewed to ensure an accurate understanding of critical product characteristics?
QP 9 | Does the plant have the latest copy of the design FMEA and was it used in conjunction with the preparation of the P-FMEA?
QP 10 | Are there consistent links between the D-FMEA, P-FMEA and control plan?
QP 11 | Have all error-proofing applications been thoroughly tested to confirm effectiveness?
QP 12 | Have all in-process quality controls been documented and incorporated into standard work instructions?
QP 13 | Is all inspection criteria well documented in standard work instructions, including check lists, exact instructions for function testing and appearance standards?
Facility Planning
FP 1 | Have plant layouts been completed that micro details every facility and equipment requirement, production operation, workplace layout and material presentation?
FP 2 | Are plant layouts being developed and reviewed with cross functional participation to ensure consensus and clear understanding?
FP 3 | Are all capital purchases being competitively quoted?
FP 4 | Are all capital requirements being thoroughly evaluated against the surplus equipment list?
FP 5 | Are inquiries being sent out to all other plants requesting surplus equipment information in the event the surplus equipment list is not up to date?
FP 6 | Have all alternative possibilities (excess equipment, local tool shops, used equipment from suppliers, going out of business auctions, etc.) been evaluated for reducing capital cost?
FP 7 | Has the capital equipment and layout plan been reviewed with company wide industrial engineering to ensure best practices and efficient utilization of equipment?
FP 8 | Has a detailed tooling and equipment plan been completed?
FP 9 | Is there a technical support plan for new equipment during launch?
FP 10 | Are modem connections being utilized by major equipment suppliers to provide 24 hours trouble shooting capability?
FP 11 | Has the emergency contact list been updated?
FP 12 | Is the tooling and equipment plan being reviewed on a weekly basis to ensure timing is on track?
FP 13 | Are there any open equipment issues which will adversely affect launch timing, quality or cost?
FP 14 | Have all equipment locations been micro detailed on plant layouts?
FP 15 | Has all equipment been validated by maintenance, production and quality personnel to ensure product integrity, safety and volume can be achieved?
FP 16 | Has a detailed facility transition plan (4 to 8 hour blocks of work) been completed to plan, coordinate and track progress?
FP 17 | Have internal maintenance resources and outside contractors been included in the facility transition planning?
FP 18 | Does everyone understand the plan and coordination requirements?
FP 19 | Has facility lighting been evaluated for necessary upgrades in critical production, quality and shipping areas?
FP 20 | Is there a plan to update and resurface all aisle line prior to production startup?
FP 21 | Has the disaster backup plan been updated for new equipment, systems and processes?
FP 22 | Is there a plan to verify the immediate readiness and effectiveness of all backup plans?
Process Planning
PP 1 | Has a process flow plan been completed or revised to reflect operation content and sequence?
PP 2 | Does the flow plan clearly demonstrate the sequence of production, testing and inspection stations?
PP 3 | Is there a plan to verify that the flow plan truly reflects the actual production and quality processes?
PP 4 | Is there a management system that links the control plan, process flow and standard work instructions to ensure of systematic and near simultaneous updating?
PP 5 | Have standard work instructions been written and / or updated and used as the basis for training?
PP 6 | Have standard work instructions been written or updated?
PP 7 | Are they prominently posted and can they be easily read by the operators?
PP 8 | Is there a managements system that systematically authorizes and updates changes to standard work instructions due to process or product changes?
PP 9 | Have labour standards been completed on every direct labour operation?
PP 10 | Is the labour standards elements of work based on the work descriptions defined in the standard work instructions?
PP 11 | Have bottleneck operations been identified and have necessary resources been deployed to analyze and resolve root causes of delays?
PP 12 | Is there an effective management system for assigning responsibilities and tracking action plans to reslove bottleneck issues?
PP 13 | Have all the shop floor scheduling documents been audited to ensure the content agrees with the BOM?
PP 14 | Is there a cross functional team that develops the micro detail planning for every production station?
PP 15 | Have repair areas been reviewed to determine if any new tooling, new equipment or rearrangements are necessary?
PP 16 | Are production operations being setup using the one step rule, that is that all direct labour operations should be setup with the objective that the direct labour operator should not move to walk any further then one step to complete their operation?
PP 17 | Is there a management system that tracks equipment and conveyor downtime?
PP 18 | Does the system include formal corrective action planning and follow-up reporting?
PP 19 | Have all tooling and assembly equipment been reviewed to ensure they incorporate the latest engineering levels?
PP 20 | Have all in process WIP (Work In Process) systems been designed with one piece flow philosophy?
PP 21 | Are all subassembly systems designed based on in sequence, synchronous flow?
Materials Planning
MP 1 | Has the FGI system been evaluated and adjusted to accommodate new part numbers, volume and mix changes?
MP 2 | Does the FGI inventory management system adequately support customer requirements?
MP 3 | Have new or modified pallets been tested in the FGI and shipping system?
Change Management
CM 1 | Is the program team and product engineering providing timely and effective information which details engineering change content, projected timing and cost?
CM 2 | Is the plant maintaining their own engineering timing matrix to ensure of comprehensive understanding and used for internal communications?
CM 3 | Does the plant engineering change control system use the company wide system for engineering changes as the basis for developing engineering change control, creation of step charts, and financial confirmation of customer and supplier pricing?
CM 4 | Is the plant confirming that all product changes are authorized with a sales authorization?
CM 5 | Is the local customer aware of impending engineering changes which affect the product?
CM 6 | Have all necessary plant tryouts been completed?
Ergonomics and Safety
ES 1 | Is P-FMEA inclusive of ergonomic evaluations following at a minimum thecompany wide standards?
ES 2 | Are machines installed CE labeled?
Note on D1: Dr. Karl Stanger: enter R, G, or Y to color the cell

## Materials
No. | Assessment question | Assessment result | RGY | Recovery planning | Respons. | Due date
General Information
GI 1 | Is a master production BOM being maintained?
GI 2 | Are all critical disciplines being kept up to date on master production BOM revisions?
GI 3 | Is the master production BOM regularly reviewed with customer information to ensure common agreement?
GI 4 | Are discrepancies between the company and customer formally documented to customer and the program team?
GI 5 | Has the master production BOM been audited to confirm that all potential build variations are accurately represented?
GI 6 | Is the engineering program team keeping the plant updated on a timely basis for revisions to the master production BOM?
GI 7 | Is new model volume and mix information being reviewed on a weekly basis?
GI 8 | Does the volume and mix agree with customer operating plans and tooling capacity constraints?
GI 9 | Are discrepancies in volume and mix being formally documented to the customer, suppliers and the program team?
GI 10 | Has the customer provided detailed scheduling information for pre-production build requirements?
GI 11 | Does the plant clearly understand delivery timing and shipping methods for each pre-production build event?
GI 12 | Have discrepancies in pre-production schedules and / or engineering levels been formally documented to the customer, suppliers and the program / engineering team?
GI 13 | Are discrepancies being formally documented to the customer for resolution regarding acceleration plans?
GI 14 | Has the customer provided detailed system fill planning, including gap planning and special shipping instructions during system fill?
GI 15 | Does the customer have any unique start up restrictions or early option batching which will affect short term mix planning?
GI 16 | Are regularly scheduled meetings being held with customer material and production control personnel to ensure all scheduling and delivery issue are being resolved?
Material Planning
MP 1 | Has a supplier contact list been prepared including emergency names and phone numbers during off-shift hours?
MP 2 | Have suppliers been contacted to communicate and / or confirm program objectives and expected bank planning?
MP 3 | Are all suppliers EDI capable for receiving release and sending ASN's?
MP 4 | Have cloth and long lead time items been reviewed to ensure that suppliers have ordered and planned sufficiently to support launch requirements?
MP 5 | Are there any known supplier capacity issues and have they been formally documented to the program team and supplier readiness?
MP 6 | Does the material releasing plan support volume and timing for line fill, FGI, extra product bank requirements, and the production acceleration plan?
MP 7 | Has requirement planning also included consideration for training material, service and any anticipated excess scrap?
MP 8 | Is there an effective communication system with the supply base to ensure that the supplier will notify the plant of any EDI communication failures or schedule concerns?
MP 9 | Has the supply base been informed formally of the plant's expectation for timely feedback?
MP 10 | Have material scheduling personnel proactively established a personal realtionship with supplier personnel to ensure cooperation and support?
MP 11 | Is there a management system in place to ensure the BOM content agrees with sales authorizations and customer requirements?
MP 12 | Is there a schedule to audit the BOM to actual assembly requirements before each major customer build event?
MP 13 | Are BOM discrepancies being formally documented to the program team?
MP 14 | Are issues being resolved in a timely manner?
MP 15 | Are there any BOM issues which will require special schedule coordination between the plant, the program team and the customer?
MP 16 | Are these issues being effectively managed?
MP 17 | Is there a management system that monitors customer releasing information on a weekly basis?
MP 18 | Do product options and mix reasonably agree with planning volumes and tooling capacities?
MP 19 | Have plausibility checks been conducted? (e.g. do release quantities for front and rear seats reasonably tie out with each other?)
MP 20 | Are planned part number changes accurately coordinated in the customer release considering both timing and volume?
MP 21 | Does the customer schedule information agree with the customer's local operating plan? (Meaning does the plant where you supply your product have the same release schedule as the OEM's head office?)
MP 22 | Have discrepancies been formally documented to the customer and the program team?
MP 23 | Is weekly schedule information being reviewed with the plant manager, controller and material manager to ensure of the integrity of information being used for financial planning?
MP 24 | Are all parent level part numbers represented on the customer release?
MP 25 | Have discrepancies been formally documented to the customer and the program team?
MP 26 | Does the plant meet regularly with customer material scheduling and receiving personnel to review and resolve issues?
MP 27 | During build out planning is the plant confirming balance to go information with the customer on a daily basis?
MP 28 | Does the customer vehicle balance to build at the broadcast trigger agree with the balance to build our product requirements?
MP 29 | Have all component part numbers been identified to specific storage and point of use locations?
MP 30 | Have all part numbers been assigned to specific material handling personnel?
MP 31 | Have all part numbers been reviewed to have specific replenishment methods determined and to establish maximum and minimum point of use inventory levels?
MP 32 | Have all material handling personnel been properly trained?
MP 33 | Are there defined methods and responsibilities for handling returnable containers from point of use to shipping?
MP 34 | Is there a process to handle damaged returnable containers or dunnage?
MP 35 | Are there defined methods and responsibilities for handling expendable containers from point of use to disposal?
MP 36 | Have all storage and point of use locations been updated with labels for part number identification?
MP 37 | Have all material handling warehouse racks, material flow through racks and material presentation racks been defined and ordered?
MP 38 | Is there a detailed plan to install all material handling equipment and is it coordinated with the facility transition plan?
MP 39 | Is there a packaging plan that considers and determines the appropriate pack type and size for every part number?
MP 40 | Is each decision for returnable packaging being based on good business case analysis?
MP 41 | Are there any significant open packaging issues? If so, are there adequate temporary packaging plans?
MP 42 | Are new shipping pallets required? If so, have they been designed,tested and ordered? Will they be available to meet shipping requirements?
MP 43 | Are there any open significant issues with shipping pallets that could affect quality or delivery requirements?
MP 44 | Is there a system for repairing damaged shipping pallets?
MP 45 | Has every part number been reviewed and evaluated for appropriate safety stock and lead times?
MP 46 | Have ship frequency, carrier selection and delivery windows been determined for each supplier?
MP 47 | Is there a management system that monitors supplier and carrier conformance to ship and delivery windows?
MP 48 | Have carrier selections and routings been optimized considering sister plant locations and corporate contracts?
MP 49 | Have milk run opportunities been evaluated? (Meaning transport pick ups combined with other pick ups)
MP 50 | Are visual management boards being used in the receiving areas to enhance communication between receiving and the material office?
MP 51 | Have changes in the customer receiving and delivery system been evaluated and tested to ensure compatibility with shipping systems?
MP 52 | Are visual management communication boards used in the shipping area to ensure shipping status with the customer is being maintained 100% of the time?
MP 53 | Have customer emergency contact list been updated?
MP 54 | Is there a shop floor management system for monitoring inventory availability for potential material shortages or surplus?
MP 55 | Is there a management system that effectively notifies salaried and hourly resources part numbers that are going obsolete?
MP 56 | Is there a management system which evaluates balance to build requirements, considering orders not yet broadcast by the customer compared to finished goods and WIP availability. A reconciliation should be completed daily beginning at least one week prior to build out. Does the material manager understand the elements of this analysis in order to make accurate projections for balance to build planning?
MP 57 | Are build out inventories well planned to ensure shortages and obsolescence is avoided?
MP 58 | Are obsolescence claims promptly reported and tracked on the open commercial issue list?
MP 59 | Is there a cycle counting procedure and has it been updated with new part numbers?
MP 60 | Does the plant have FIFO systems included in their material flow planning?
MP 61 | Is there a management system which ensures periodic review of inventories for aged or obsolete materials?
MP 62 | Is there a managements systems for inventory and replenishment of non-BOM general stock items such as glue, tape, hogrings, etc.?
MP 63 | Have all training materials been prominently identified to ensure they do not get mixed with good parts?
MP 64 | Is there a management system in place that ensures all customer and supplier cum variances are being resolved on a weekly basis?
MP 65 | Will a finished product bank be required? If so, has a detailed plan been established for ordering material, building and and storing the product?
MP 66 | Is there a management system in place to manage and segregate new engineering level or tryout materials?
MP 67 | Is there a management system for identifying, removing, quarantining, counting and reporting obsolete materials?
MP 68 | Have customer service parts requirements been established for the program?
MP 69 | Have initial service parts requirements been planned and / or shipped?
MP 70 | Have service parts procedures been established for production, quality and materials?
MP 71 | Have customer service part numbers been released and are EDI systems in place for releasing, ASN's and invoicing?
Change Management
CM 1 | Has impending engineering change timing been confirmed with affected suppliers?
CM 2 | Is a product content change summary report being prepared and published prior to each major build event for planning and training purposes? The report summary should include information regarding timing, parts and suppliers affected, reason for the changes, description of the changes, coordination requirements and obsolescence.
Note on D1: Dr. Karl Stanger: enter R, G, or Y to color the cell

## Information Technology
No. | Assessment question | Assessment result | RGY | Recovery planning | Respons. | Due date
Process Planning
PP 1 | Have all shop floor scheduling systems been defined and / or modified including pick list, build labels, shipping labels, printer locations, IT systems, etc.?
PP 2 | Have all shop floor systems been tested and validated for content accuracy?
PP 3 | Have all critical salaried and hourly personnel been trained in the shop floor scheduling systems?
PP 4 | Are the shop floor systems being created and utilized during pre-production build events?
PP 5 | Are contingency plans in place with the customer to ensure broadcast failures can be supported with alternative electronic or manual systems?
Material Planning
MP 1 | Has electronic broadcast information been tested during the pre-production build process?
MP 2 | Has FGI and shipping system error-proofing been tested to ensure of effectiveness?
Infrastructure/Hardware
IH 1 | Are all systems connected to the LAN / WAN?
IH 2 | Has electronic broadcast information been established and tested during the pre-production build process?
IH 3 | Has a power supply (UPS) been installed and tested?
IH 4 | Are all label printers in place and tested?
IH 5 | Are all scanners in place and tested?
IH 6 | Have all monitors been installed and tested?
Security
S 1 | Does a contingency plan exist, covering all internal processes?
S 2 | Are contingency plans in place with the customer to ensure broadcast failures can be supported with alternative electronic or manual systems?
S 3 | Are DRP (Disaster recovery plan) procedures defined and tested?
Organization
O 1 | Are all responsibilities defined?
O 2 | Is the IT staff trained?
O 3 | Have all users been trained on the applications they utilize?
O 4 | Is there a resource scheduling to guarantee permanent support?
O 5 | Is the documentation up to date and available?
Applications
A 1 | Have master data been checked concerning completeness and accuracy (items, BOM, contracts, cost price)?
A 2 | Are all processes defined, documented and tested?
A 3 | Have all interfaces been tested?
A 4 | Has an integration test been performed?
A 5 | Have all output documents been tested (labels, pick lists, shipping documents, etc.)?
Note on D1: Dr. Karl Stanger: enter R, G, or Y to color the cell

## Finance
No. | Assessment question | Assessment result | RGY | Recovery planning | Respons. | Due date
General Information
GI-A-1 | Is product pricing information being timely and accurately communicated from the program team?
Are issues being formally documented to the program team?
GI-A-2 | Is there a financial system that tracks the COGS margins against the financial models?
Are differences investigated and understood?
Are differences formally documented to the program team?
GI-A-3 | Is there a financial system that quantifies and tracks all open commercial issues with the program team?
GI-A-4 | Is there a financial system that tracks the costed BOM against the quoted BOM?
Are differences formally documented to the program team?
GI-A-5 | Is component pricing information being timely and accurately communicated from the program team?
Are issues being formally documented to the program team?
Is there a financial system that tracks the product pricing model against the customer PO's?
GI-A-6 | Are differences formally documented to the program team?
Facility Planning
FP-B-1 | Has the program approval request been submitted and approved?
FP-B-2 | Has the capital spending plan been calendarized to optimize cash flow?
FP-B-3 | Is there a check and balance system in place between plant engineering and finance to track program approval request expenditures against program approval request authorizations?
Process Planning
PP-C-1 | Does the manning plan agree with budget and / or financial forecast?
PP-C-2 | Have all launch related salaried and hourly cost been incorporated in budgets and / or financial forecast?
PP-C-3 | Have the resources for containment been included in the budget and / or financial forecast?
Material Planning
MP-D-1 | Have all supplier PO's been issued?
Are missing or inaccurate PO's being formally documented to the program team and purchasing?
MP-D-2 | Has Finance received customer PO's for service parts?
MP-D-3 | Have open issues on service parts been formally documented to the program team?
Note on D1: Dr. Karl Stanger: enter R, G, or Y to color the cell

## Human Resources
No. | Assessment question | Assessment result | RGY | Recovery planning | Respons. | Due date
General Information
GI-A-1 | Are there any labour relations issues likely to affect launch performance?
Have labour agreements such as rotation plocies, overtime agreements, shift transfer rights, bumping rights, etc. been reviewed to ensure they do not interfere with training and launch success?
Have temporary moratoriums been discussed with the union leadership to avoid interferences?
GI-A-2 | Have temporary salaried positions (contract) been identified, timed and planned?
GI-A-3 | Have organization charts been updated to reflect planned changes?
Process Planning
PP-B-1 | Does the hiring plan include a detailed screening of all new employees?
PP-B-2 | Does the hiring process include formal employee orientation and training prior to specific operation assignment?
PP-B-3 | Has the hiring plan been reviewed with the union leadership?
PP-B-4 | Has an agreement been established with the unionleadership on the utilization of contract employees?
PP-B-5 | Have temporary staffing requirements been defined and planned?
PP-B-6 | Is there a management system to ensure that new or temporary operators are not left unattended?
PP-B-7 | Is there a union / management process to resolve standards disputes before they become major obstacles to meeting program objectives?
Note on D1: Dr. Karl Stanger: enter R, G, or Y to color the cell

## Quality
No. | Assessment question | Assessment result | RGY | Recovery planning | Respons. | Due date
General Information
GI 1 | Has an appearance standard been completed and, if so, can the standard be produced at volume?
GI 2 | Has the appearance manual standards been approved by the customer engineering and quality personnel?
GI 3 | Have boundary samples been produced and are they being used to train and monitor product conformance to the sample?
GI 4 | Has the plant initiated formal reviews with the local customer to ensure they are aware of product and process launch readiness?
GI 5 | Have new product characteristics and features been clearly defined and understood?
GI 6 | Have pictoral charts and / or diagrams been developed to assist with communications, training and visual aids?
GI 7 | Have new product features and functions been reviewed with customer plant personnel on all shifts?
Quality Planning
QP 1 | Has the control plan been completed with a cross functional team?
QP 2 | Is the control plan updated as design changes and customer expectations are revised?
QP 3 | Is the control plan and activities reviewed on a scheduled basis to ensure appropriate conformance to requirements?
QP 4 | Is the control plan being followed?
QP 5 | Does the control plan include variable data measurements for critical characteristics and are they capable?
QP 6 | Are there alternative plans for characteristics that are not capable?
QP 7 | Has a process audit plan been developed for pre-production requirements?
QP 8 | Has an enhanced process audit schedule been developed for increased audit frequency during the acceleration period?
QP 9 | Are there process audits based on the details of the standard work instructions and quality expectations?
QP 10 | Is there a management process that monitors and follows up on process audit deficiencies for determining additional training requirements, standard work revisions or employee counseling?
QP 11 | Has a product audit been established?
QP 12 | Are key characteristics verified?
QP 13 | Is there a cross functional and hourly participation in the product audit reviews and is the audit area in a highly visible area?
QP 14 | Is product audit information documented and tracked over time?
QP 15 | Is the information prominently displayed for employee awareness?
QP 16 | Are customer PPAP events recognized as formal events and planned accordingly?
QP 17 | Are plans made to effectively host customer representatives?
QP 18 | Is PPAP product pre-reviewed with the plant manager and staff to ensure the very best product is represented?
QP 19 | Is the product reviewed with the customer in a clean, well lighted area to ensure maximum receptiveness of the customer?
QP 20 | Are all PPAP documents prepared in advance with appropriate detail immediately available if requested?
QP 21 | Is the entire workforce informed of a customer PPAP event to ensure maximum awareness?
QP 22 | Is there a supplier PPAP plan that supports the plant and program objectives?
QP 23 | Is the plant actively involved in the supplier PPAP planning and processing?
QP 24 | Have customer materials reporting requirements been completed using the international materials data system (IMDS)?
QP 25 | Are parts identified with appropriate ISO marking codes in accordance with customer requirements?
QP 26 | Does the plant monitor progress on all supplier parts that have been less then fully PPAP'ed?
QP 27 | Are there any open supplier PPAP issues which will significantly affect launch timing, quality or cost?
QP 28 | Have these issues been formally documented to the program team and purchasing?
QP 29 | Have all inspection personnel been properly trained?
QP 30 | Is there a gate or alarm system which tracks defect data and signals alarms when certain pre-set criteria es exceeded? Is it being effectively used forcontinuous improvement?
QP 31 | Is there an effective, real time communications loop between inspection and production processes?
QP 32 | Is quality data collected, analyzed, prioritized and utilized for problem solving and continuous improvement?
QP 33 | Is there a management system that ensures all quality alerts and lessons learned from other sources are being incorporated in the plant production and quality systems?
QP 34 | Is there a management system which formally defines problem solving activities and methods for both short term corrective actions and permanent corrective actions?
QP 35 | Is the production process yielding the expected quality results station to station? If not, is there a formal improvement plan?
QP 36 | Have all test systems and equipment been validated?
QP 37 | Have gage R&R studies been completed and results considered in the control plan?
QP 38 | Does the plant have tools, gages or a plan that provides a method to periodically verify vehicle integrity? (This is especially critical when there are disputes concerning our product to vehicle interfaces.)
QP 39 | Have all quality personnel been properly trained in the use of test and inspection equipment?
QP 40 | Has all test and inspection equipment, tools and gages been properly calibrated?
QP 41 | Is all required customer documentation being collected and archived? Has the data collection system been tested?
QP 42 | Is there an enhanced receiving inspection plan for pre-production and early launch?
QP 43 | Have critical parts been identified for 100% inspection until capability is established?
QP 44 | Is ther a secured quarantine area clearly identified for suspect parts?
QP 45 | Is there an effective communication system between quality and materials to ensure rejected or supect parts are excluded from inventory availability?
QP 46 | Are critical suppliers scheduled to be available during launch to assist with confirming the integrity of their product and be immediately available for problem solving if there are issues?
QP 47 | Is the plant being kept abreast of supplier issues which may adversely affect the launch?
QP 48 | are there any open issues which could significantly affect launch timing, quality or cost?
QP 49 | Have these issues been formally documented to the program team, the supplier readiness manager and purchasing?
Process Planning
PP 1 | Has a schedule of support at the customer been considered?
PP 2 | Has a detailed pre-production containment plan been established to guarantee no appearence or functional defects?
PP 3 | Have specific quality gates been established which monitor and gather predefined information?
PP 4 | Are containment operators properly trained and are the same operators assigned daily?
PP 5 | Is defect data being consolidated by shift and gate location and is the information being effectively disseminated?
PP 6 | Are defects found in the containment process being used as lessons learned and are initiating formal documentation for corrective action to product or process designs?
PP 7 | Does the pre-production containment process include enhanced documentation of product compliance through digital photos or video?
PP 8 | Has a production containment plan been completed to ensure defects are not passed to the customer?
PP 9 | Are extraordinary containment efforts being deployed during low volume acceleration periods?
PP 10 | Are production operators being given the opportunity to spend time in the containment areas to understand the defect issues?
PP 11 | Does the containment plan provide for immediate feedback loops to operators for critical defects?
PP 12 | Are containment issues being used for lessons learned for updating the P-FMEA and error-proofing corrective actions?
PP 13 | Is there a specific training plan to train containment operators?
PP 14 | Is there an effective management system for evaluating containment data and trends?
PP 15 | Is there a defined exit plan for containment activities based on time or performance?
PP 16 | Is there a management tracking system that identifies, documents, and prioritizes all quality and production problems by operation?
PP 17 | Is there an effective method for assigning responsibilities for corrective action planning?
PP 18 | Are there startup scrap procedures in place to quickly identify and resolve issues?
PP 19 | Are there defined and separate containers for non-conforming parts?
Note on D1: Dr. Karl Stanger: enter R, G, or Y to color the cell

## Maintenance
No. | Assessment question | Assessment result | RGY | Recovery planning | Respons. | Due date
Facility Planning
FP 1 | Has backup tooling and equipment been planned and is it readily accessible?
FP 2 | Have preventive maintenance procedures been updated for new tooling and equipment?
FP 3 | Is there a training plan to train maintenance personnel on new tooling and equipment?
FP 4 | Have spare part requirements been identified and planned?
FP 5 | Has utility accessibility been pre-planned for tooling and equipment installations?
FP 6 | Does every piece of equipment have a package that includes schematics, troubleshooting decision trees, PM requirements, PM and repair documentation, and shut-down and start-up procedures?
FP 7 | Is there an inventory checklist of critical back-up equipment and spare parts for availability and location?
FP 8 | If equipment or parts are not currently available is there a procurement plan identified with timing?
Note on D1: Dr. Karl Stanger: enter R, G, or Y to color the cell

## Production
No. | Assessment question | Assessment result | RGY | Recovery planning | Respons. | Due date
General Information
GI 1 | Does the plant have a formal workplace organization and housekeeping plan?
Process Planning
PP 1 | Have manning requirements been established in detail from the start of pre-production training through production acceleration?
PP 2 | Has a hiring plan been developed to meet the manning plan requirements?
PP 3 | Have rotation plans been developed for critical ergonomic jobs and has the plan been reviewed with the union leadership?
PP 4 | Has an agreement been established with the union leadership to define job placement and manning flows?
PP 5 | Does the production build plan target volume capability objectives based on rate per hour at least 2 weeks ahead of customer requirements?
PP 6 | Is there a managments system in place to track the production capability progress to the plan on a daily and shift basis?
PP 7 | Has a pre-production training plan been detailed for product and process knowledge?
PP 8 | Is there a training matrix that tracks employee competency for each job?
PP 9 | Are employees aware of pre-production training strategy, plans, and timing?
PP 10 | Has a production training plan been completed with the objective to have every operator capable of satisfying quality requirements at rate?
PP 11 | Is there a formal operator certification plan that tracks and documents operators knowledge and performance capability?
PP 12 | Is the operator certification status updated frequently and is it used by production management for monitoring operator progress and job placement?
PP 13 | Is there a management system that tracks each operator's utilization to the takt time?
PP 14 | Have line balance objectives been established?
PP 15 | Is there a detailed plan that schedules power builds and mini internal Run @ Rates prior to customer events?
PP 16 | Do the power builds and internal Run @ Rates include a disciplined method for identifying throughput issues?
PP 17 | Is there a management system that tracks production performance to customer requirements on an hourly basis?
PP 18 | Is there a management validation system (walk the floor) to ensure each operation is prepared and capable to meet quality and volume requirements?
Note on D1: Dr. Karl Stanger: enter R, G, or Y to color the cell

## EHS
No. | Assessment question | Assessment result | RGY | Recovery planning | Respons. | Due date
General Information
GI 1 | Have all process related material safety data sheets been reviewed for regulatory purposes?
Environmental
EN 1 | Have air permits been issued or updated such that the process can be installed and operated?
EN 2 | Are there any waste water streams from the process and if so, have all waste water streams been identified and applicable permits for discharge been upgraded or applied for?
EN 3 | Have all by-product (waste) streams generated from the process been properly characterized for disposal or recycling purposes?
EN 4 | Has an ISO 14001 aspects and impacts assessment of the process been completed?
Health and Safety
HS 1 | Are all pulleys, belts, chains, sprockets and other power transmission sources guarded? (in conformance with local legislation)
HS 2 | Are operations that have rotating partts, pinch points, nip points, etc. guarded? (in conformance with local legislation)
HS 3 | If machines are designed for a fixed location, are they securely anchored?
HS 4 | Is ther a single, lockable, clearly marked electrical power disconnect?
HS 5 | Are isolation valves for air, steam and other utilities accessible and marked?
HS 6 | Is there an adequate number of properly located manual reset emergency stops?
HS 7 | Have equipment specific lockout procedures been put in writing and are they easily accessible?
HS 8 | Have employees, who will perform repair, maintenance and servicing operations, been trained in the equipment specific lockout before they perform this type of operation?
HS 9 | Are the floors and aisles clear of trip hazards? (electrical cords and pnumatic hoses must be up off of the floor)
HS 10 | Are changes in floor elevations clearly identified by color coding, if necessary?
HS 11 | Does equipment produce discharges onto the floor that are not adequately contained?
HS 12 | Is all conduit, cable and wire properly attached to all supports and tightly connected to junction and outlet boxes?
HS 13 | Are all unused openings in junction boxes plugged?
HS 14 | Are all electrical boxes closed?
HS 15 | If explosion proof electricals are involved, do all devices meet the appropriate class and division requirements?
HS 16 | Are all controls properly labeled?
HS 17 | Do electric push buttons have correct color coding? (only stop button should be red in colour)
HS 18 | Are all electrical panel areas accessible and clear of obstructions?
HS 19 | Are platforms that are more than 1,21m above the floor level equipped with standard railing and toe boards?
HS 20 | Are fixed ladders secured against movement?
HS 21 | Do stairs have handrails and midrails?
HS 22 | Do crossover conveyors have handrails?
HS 23 | Are there any special personal protective equipment reqirements for the equipment or operations as determined by an assessment?
HS 24 | Has appropriate personal protective equipment been provided to employees?
HS 25 | Have employees been trained in proper use and care of protective equipment?
HS 26 | Is there a system to ensure that risk assessments (job safety analysis) are completed for each work station?
HS 27 | Have ergonomic risks associated with the tasks been evaluated from a standpoint of force, frequency, posture and duration?
HS 28 | Are controls easy to reach and laid out in a manner that makes them easy to read and use for the equipment operations?
HS 29 | Have operators been thoroughly trained in the operation of equipment, manufacturer's requirements for operation and maintenance equipment safeguards, and warning systems?
HS 30 | Are there sharp edges on the equipment / product that could cut or injure operators or others passing by the equipment?
HS 31 | If any chemical agents are required for the operation, servicing or maintenance of the equipment, have material safety data sheets been obtained and reviewed for special requirements such as ventilation, storage, personal protective equipment, medical surveillance, etc.?
HS 32 | Have employees been trained in the chemical hazards?
HS 33 | Does the equipment / operation emit any hazardous chemicals, excessive noise levels, radiation, heat or other physical hazards as determined by an industrial hygiene evaluation?
HS 34 | Are there hot surfaces? If so, are they guarded and labeled?
HS 35 | If ventilation systems are required on the equipment, are flow indicators provided and have operators been trained in the use and interpretation of them?
HS 36 | Are low alarms installed on critical ventilation systems?
HS 37 | Does the equipment / process present any inherent fire hazards such as open flame, flammable liquids, solids and gases, etc.? Are these hazards properly controlled by safeguards?
HS 38 | Has the insurance consulting service been contacted to provide input regarding sprinklers and other controls?
HS 39 | Are fire extinguishers required?
HS 40 | Have employees been trained in emergency shut down procedures?
Note on D1: Dr. Karl Stanger: enter R, G, or Y to color the cell

## Lean Manuf.
No. | Assessment question | Assessment result | RGY | Recovery planning | Respons. | Due date
Standardized Work
SW 1 | Are the work standards being developed by the people who are performing the tasks?
SW 2 | Is all standardized work understood and being followed by all operators (on all shifts)?
SW 3 | Has the distance the operators travel to get and install parts been minimized to reduce waste of motion?
SW 4 | Does the material presentation allow for ease of access, minimization of space and reduction of waste of motion?
SW 5 | Have the operators trips to bench and material been minimized to two (2) or less per cycle?
SW 6 | Have operators decisions been minimized to decrease delays and/or mistakes?
SW 7 | Has the handling of non-productive materials by the operators been limited?
SW 8 | Are the operators movements unrestricted, unobstructed and not in conflict with other operators?
SW 9 | Have the machines, tools and equipment been located to minimize space utilization and reduce waste of motion?
SW 10 | Do the written standardized work instructions displayed at each operation contain correct information?
SW 11 | Have the operator and machine cycle times been balanced to minimize operator wait time?
SW 12 | Have machines been equipped with part ejectors or transfer devices to minimize waste of motion?
SW 13 | Do operators and machines cycle independently?
SW 14 | Are the best work methods being used by all operators (on all shifts)?
SW 15 | Is the standardized work data current, properly maintained and continuously improved?
SW 16 | Is the standardized work data used by the indirect labor work functions?
SW 17 | Is the visual line balance process (i.e. display wall approach) used to distribute the work elements between operators?
SW 18 | Is the standardized work content and development process periodically assessed to evaluate effectiveness?
Workplace Organization
WO 1 | Have the Plant Workplace Organization guidelines (Five S's) been developed?
WO 2 | Have the Assessment and Review processes been systemized to evaluate compliance to the Five S's?
WO 3 | Are "cleanliness" requirements being properly maintained on all shifts?
WO 4 | Are "organization" requirements being properly maintained on all shifts?
WO 5 | Are effective TPM Housekeeping processes in place on all shifts?
WO 6 | Is all material inventory stored and arranged in an organized and safe manner?
WO 7 | Is the safety and emergency equipment located and organized in a way to assure easy access and use?
WO 8 | Has effective employee training and awareness been provided?
WO 9 | Has Five "S" Workplace Organization training been provided and are improvement activities in place?
Audio and Visual Controls
AV 1 | Has the Flow Rack for small material containers been clearly marked with labels to identify the specific spot where parts are to be located?
AV 2 | Have the Central Material Storage locations for bulk materials been clearly marked with labels to identify the specific spot where parts are to be located?
AV 3 | Has all non-conforming material been visually identified?
AV 4 | Has all miscellaneous material been identified?
AV 5 | Have all storage areas, traffic aisles and pedestrian walkways been visually identified?
AV 6 | Do material container safe stacking heights have visual indicators and/or instructions displayed?
AV 7 | Are Work-in-Process Buffer, bank location and size limitations visually identified?
AV 8 | Are truck delivery dock receiving times and status visually displayed?
AV 9 | Do safety related visual aids provide alerts of potential hazards?
AV 10 | Are Total Preventive Maintenance schedules and status visually displayed?
AV 11 | Do Operations Certification display boards contain all necessary information?
AV 12 | Are Key Point charts displayed on the Operation Certification display boards (as required)?
AV 13 | Do Andon boards, lights and audio signals communicate operator calls for assistance and operating status?
AV 14 | Do Andon station lights display operator call locations and system operating status?
AV 15 | Do Error Proofing visual and audio signals communicate operating status?
AV 16 | Do Product Quality and Productivity display boards communicate current performance data?
AV 17 | Do Problem Solving display boards communicate status of continuous improvement activity?
Operation Certificates
OC 1 | Do Certification display boards contain all necessary information?
OC 2 | Are Key Point charts displayed on the Operation Certification display boards (as required)?
OC 3 | Is the Protective Equipment and Apparel Chart posted and maintained on the Operation Certification board?
OC 4 | Is the Safety Certification Checklist posted and maintained on the Operation Certification board?
OC 5 | Is the Operation Performance Checklist posted and maintained on the Operation Certification board?
OC 6 | Is there a process in place to periodically update the Operation Certification boards and review content with employees?
Internal Pull and Material Conveyence
PM 1 | Is all material replenished using a pull signal initiated by the operator (user)?
PM 2 | Are Kanban Cards used to replace material in small hand delivered containers?
PM 3 | Are Kanban Cards standardized and do they contain specific information?
PM 4 | Are Kanban posts, boxes or slide chutes used to hold mailed cards?
PM 5 | Are standardized routes used to deliver small containers and pick up empty containers/dunnage?
PM 6 | Is material replenished Just in Time (pulled) based on consumption?
PM 7 | Is an electronic pull signal (Andon) used to replenish large containers?
PM 8 | Do operators order bulk material at the designated time?
PM 9 | Do bulk delivery material handlers promptly replenish parts ordered via electronic signals?
PM 10 | Are electronic Andon control boards or screens used to track orders?
PM 11 | Is a Dolly exchange used to replace consumed parts?
PM 12 | Is a production count used to replace material?
PM 13 | Is material kitted to small containers or multi-part dollies to reduce the size of containers and quantity presented to the operator?
PM 14 | Is material replenished in build sequence?
External Pull and Transportation System
PT 1 | Are parts ordered based on actual consumption?
PT 2 | Material is received when needed at a specific time and receiving?
PT 3 | Are receiving areas visually managed?
PT 4 | Do transportation logistics optimize pick-ups, deliveries and freight?
PT 5 | Has a communication system been established to rapidly provide advance warning and/or feedback?
Central Material Storage
MS 1 | Are the Centralized Material Storage areas used to temporarily hold bulk and small containers?
MS 2 | Are the Centralized Material Storage areas well organized and visually managed?
MS 3 | Is there a process in place to assure that the Centralized Material Storage areas are being properly managed and maintained?
MS 4 | Are the Centralized Material Storage areas inventory levels being maintained within controlled limits?
MS 5 | Are small containers stored to in a way to assure FIFO flow and are organized in one specific location that is visually managed?
MS 6 | Are the Centralized Material Storage areas for small containers managed by a dedicated resource?
MS 7 | Are bulk containers stored to in a way to assure FIFO flow and are organized in one specific location that is visually managed?
MS 8 | Are the empty returnable bulk containers stored/staged within the Central Material Storage area?
MS 9 | Are the empty returnable small containers sorted in a dedicated area?
MS 10 | Is the fork lift traffic restricted to receiving docks and "put away" storage aisles within the Central Material Storage areas?
Lean Containers and Packaging
CP 1 | Has a Plan for every Part (PFEP) been created for all components for new model programs (material packaging engineers)?
CP 2 | Has a Plan for every Part (PFEP) been created for all components for current model programs (plant evaluation)?
Andon
A 1 | Does the Andon system hardware and infrastructure provide status at a glance and line stop capability at fixed position locations?
A 2 | Do Andon display boards provide status at a glance operating system and call status?
A 3 | Do Andon station (stacked) lights provide status at a glance to quickly locate specific operators requesting support?
A 4 | Are Andon cords and buttons easily accessible at each operation?
A 5 | Is the Fixed Position Stop (FPS) capability that is linked to the Andon call system fully operational?
A 6 | When activated, do the Andon systems audio signals (music/tones) provide audible signals?
A 7 | Do the self directed work groups use Andon to build quality in station?
A 8 | Does the Andon system functionality provide the ability to activate and deactivate FPS?
A 9 | Is the associates to team leader ratio sized to assure rapid response?
In-Process Quality Audit
QA 1 | Are there In-Process Quality Verification (QV) stations in place to perform standardized inspections?
QA 2 | Are there visual display boards in place at all QV stations to track discrepancies?
QA 3 | Is there a communication and awareness process in place to rapidly communicate quality information and receive corrective action status?
QA 4 | Are the Standardized Work Instructions (SWI) written and used to perform inspections?
QA 5 | Are the quality alarm thresholds established as control limits?
QA 6 | Are the Shipping Quality Standards (SQS) defined, written, communicated and enforced?
QA 7 | Are successive (layered) inspections performed by the operators?
Continuous Improvement Process
CI 1 | Is there a structured and standardized process established to assess work activities and make improvements on a continual basis?
CI 2 | Have teams been fully trained to understand the Continuous Improvement Process and are they responsible for driving the process?
CI 3 | Have Continuous Improvement plans, goals and objectives been established?
CI 4 | Are Improvement Ideas replicated?
CI 5 | Is a plan defined for every operation and component?
CI 6 | Have work elements/functions been evenly distributed, redistributed, combined, simplified, or eliminated?
CI 7 | Is a Continuous Improvement (Kaizen) shop in place and equipped?
Problem Solving
PS 1 | Is there a Practical Problem Solving (PPS) process in place and are employees actively engaged in on-going activities?
PS 2 | Is Practical Problem Solving used first as a means of resolving issues before higher level tools are applied?
PS 3 | Is on-going Practical Problem Solving training provided to all employees?
PS 4 | Is there a communication process in place to transfer information from problem solving activities?
PS 5 | Is top leadership actively involved in mentoring and conducting regular progress reviews?
PS 6 | Are repetitive and recurring tracked and Problem Solving conducted?
PS 7 | Are Problem Solving goals and objectives set for all levels of the organization?
Total Productive Maintenance
TM 1 | Is the TPM Process well defined, written, communicated and performed properly?
TM 2 | Is there a tracking system in place to monitor TPM performance based on defined metrics?
TM 3 | Does Leadership understand, support and review TPM activities?
TM 4 | Are all employees fully trained on the TPM Process, practices, roles, responsibilities, safety and ergonomic requirements?
TM 5 | Do Self Directed Work Groups (operators) perform minor and routine preventative maintenance functions?
TM 6 | Are the Self Directed Work Groups (operators) TPM tasks and responsibilities written, communicated and tracked?
TM 7 | Do skilled trades perform technical maintenance functions?
TM 8 | Are the skilled trades technical TPM's monthly, weekly and daily inspections and tasks visually displayed?
TM 9 | Are TPM technical memory logs maintained?
TM 10 | Are the skilled trades fully trained in the Predictive Technologies?
TM 11 | Do the operators and skilled trades have the ability to easily monitor the status of equipment functions, pressures, fluids, temperatures, etc.?
TM 12 | Are TPM activities continuously evaluated and improvements made?
Error Proofing
EP 1 | Have workers been trained in the basics of error-proofing? Is there a team responsible for analyzing production defects and identifying error proofing opportunities?
EP 2 | Have error proofing devices and methods been implemented and/or are they being developed to eliminate the top production defects for each work area in the plant?
EP 3 | Have error proofing devices and methods been applied to both manual operations and automated processes?
EP 4 | Have the error proofing devices that have been installed monitored for effectiveness and are maintained and kept in sound working condition?
EP 5 | Has analysis been conducted on parts and components to identify design opportunities to eliminate waste and improve productivity?
EP 6 | Are operators able to stop the line when a defective unit is found or when they cannot complete their process according to the SOP?
EP 7 | Have manual processes or tasks been equipped with mechanical checks to aid human judgment whenever possible?
EP 8 | Are processes equipped with call lights or signals (andons) that workers and machines actuate to call for assistance when a problem is encountered?
Quick Changover
QC 1 | Are all changeovers scheduled in advance and communicated so that workers on the team know the days changeover schedule?
QC 2 | Have quick change over teams received training on change over time reduction procedures and are they actively improving change over methods?
QC 3 | Have set-up activities been subject to detailed process analysis techniques such as motion and time study, videotaping to identify waste, etc?
QC 4 | Is change over time, both internal and external, visibly tracked at each work station where change overs are performed?
QC 5 | If new change over procedures are developed, are they standardized and replicated in other areas of the plant?
QC 6 | Have special tools and/or equipment been developed and implemented to reduce the time and labor involved in the change over process?
QC 7 | Are all of the dies, fixtures, tools, fasteners, materials, parts, raw stock, etc. needed for the next production run prepared in advance to reduce change over times?
QC 8 | Are all dies, fixtures and change over time stored in a neat, orderly fashion when not in use and maintained in good working condition?
Note on D1: Dr. Karl Stanger: enter R, G, or Y to color the cell

## Matrix
|  | Launch Manager | Industrial Engineering | Materials | Information Technology | Finance | Human Resources | Quality | Maintenance | Production | EHS | Lean Manufacturing
GI | General Information | x | x | x |  | x | x | x |  | x | x
QP | Quality Planning | x | x |  |  |  |  | x
FP | Facility Planning | x | x |  |  | x |  |  | x
PP | Process Planning | x | x |  | x | x | x | x |  | x
MP | Material Planning | x | x | x | x | x
CM | Change Management | x | x | x
ES | Ergonomics and Safety |  | x
IH | Infrastructure and Hardware |  |  |  | x
S | Security |  |  |  | x
O | Organization |  |  |  | x
A | Applications |  |  |  | x
EN | Environmental | [9 empty] | x
HS | Healths and Safety | [9 empty] | x
SW | Standardized Work | [10 empty] | x
WO | Workplace Organization | [10 empty] | x
AV | Audio and Visual Controls | [10 empty] | x
OC | Operation Certificates | [10 empty] | x
PM | Internal Pull and Materials Conveyence | [10 empty] | x
PT | External Pull and Transportation System | [10 empty] | x
MS | Central Material Storage | [10 empty] | x
CP | Lean Containers and Packaging | [10 empty] | x
A | Andon | [10 empty] | x
QA | In-Process Quality Audit | [10 empty] | x
CI | Continuous Improvement Process | [10 empty] | x
PS | Problem Solving | [10 empty] | x
TM | Total Productive Maintenance | [10 empty] | x
EP | Error Proofing | [10 empty] | x
QC | Quick Changeover | [10 empty] | x